## Slide 1: Strengthening Regional Cooperation on Skills Development under the CAREC Program: Key Progress, Challenges, and Opportunities for Collaboration Inception Meeting and International Expert Roundtable 30–31 May 2022, Tbilisi, Georgia
RETA 6806:
Project Overview
Guntur Sugiyarto Principal Economist Regional Cooperation and Operations Coordination Division, CWRC, ADB

## Slide 2: Presentation Outline
Background
The Technical Assistance (TA)
  Objectives
  Impact and Outcome
  Key Activities
  Milestones
  Next steps

## Slide 3: Background
Part of the Human Development cluster: CAREC 2030 strategic framework.
A direct follow-up to the recommendations of the 2019 scoping study the CAREC Secretariat recommending a phased approach:
    Short term: establishing of regional expert groups on improving quality standards and harmonization, academic and skill mobility, and labor market information.
    Long term: forming sector committee and a strategic framework for regional cooperation and investment financing.

## Slide 4: Rationale of the TA
Increasing job disruptions as countries move closer to Industry 4.0.
Covid-19 pandemic’s long-term effects on the labor market as tens of millions of jobs lost worldwide to never return again, fundamentally changing the way many of us work
Need to ensure the competitiveness of CAREC member countries via improving labor force quality
Risk of being left behind as its talented workforce leave permanently to work elsewhere
A proactive regional policy aimed at improving the labor force quality and facilitating skill mobility to support circulation and recognition of skills could mitigate this risk.

## Slide 5: Objectives
The TA will improve four key areas of:
standardization and harmonization in higher education,
standardization and harmonization in TVET,
governance and regulation of recruitment systems, and
development of labor market database and information system.
The TA’s main focus is to improve systems and governances at the country and regional levels, considering global best practices, the countries’ diverse backgrounds, and geographical context, as well as the countries’ agendas, key stakeholders’ requests from the previous consultations, and other previous and ongoing initiatives to ensure strong buy-in and synergy while avoiding duplication.

## Slide 6: Impact and Outcome
Impact
  Human development improved through increased quality, mobility, and productivity of the labor force of the CAREC countries
Outcome
  Regional cooperation and integration in the CAREC region strengthened through better utilization and allocation of human resources, in line with the CAREC 2030 Strategy and Strategy 2030 Operational Plan

## Slide 7: Outputs, Methods, and Activities
Output 1: Standardization and harmonization in higher education strengthened
  collaboration between universities in the CAREC region and top leading universities in Japan and/or the rest of the world;
  establishing a cross-country interagency working group comprising of women and men professionals in higher education; and
  developing bilateral and/or regional higher education standardization and harmonization frameworks.
  setting up a regional university network initiative;

## Slide 8: Outputs, Methods, and Activities
Output 2: Standardization and harmonization in TVET strengthened
collaborations with Japanese and/or top global leading institutions, including through encouraging faculty, student, and trainee exchanges comprising both women and men, and incorporating distance learning;
a toolbox of training manuals for specific occupations such as tourism professionals and other occupations favoring women;
cross-country interagency working group comprising of women and men professionals in TVET;
bilateral and/or regional TVET standardization and harmonization frameworks; and
bilateral and/or regional agreements for institutional collaborations for selected occupations

## Slide 9: Outputs, Methods, and Activities
Output 3: Governance and regulation of recruitment systems improved
conduct comprehensive assessments of the cross-border recruitment rules and regulations of the private recruitment agencies, government-to-government, and business-to-business schemes for more efficient and transparent labor mobility in the region.

## Slide 10: Outputs, Methods, and Activities
Output 4: Labor market database and information system developed
facilitate regular and comprehensive assessments on job and labor market issues including on social protection and skill mobility to contribute to the evidence-based decision-making process by providing key labor market information and labor characteristics across countries.

## Slide 11: Milestones
Activity | Milestones
1. Standardization and harmonization in higher education strengthened | Q3 2022–Q2 2024
1.1 Collaborate with top universities, including from Japan, for various programs | Q3 2022–Q1 2024
1.2 Establish an interagency working group on higher education standardization and harmonization | Q4 2022–Q4 2022
1.3 Initiate the establishment of the university network in the CAREC region | Q4 2022–Q4 2023

## Slide 12
Activity | Milestones
2. Standardization and harmonization in technical and vocational education and training strengthened | Q3 2022–Q2 2024
2.1 Develop toolboxes for tourism professionals and another selected occupation | Q1 2023–Q1 2024
2.2 Establish TVET institutions networks and bilateral and/or regional standardization system for a selected occupation | Q4 2022–Q4 2024
2.3 Undertake institutional arrangements through a bilateral and/or regional framework agreement | Q4 2022–Q4 2023

## Slide 13
Activity | Milestones
3. Governance and regulation of recruitment systems improved | Q4 2022–Q2 2024
3.1 Assess laws and regulations governing the private recruitment agency, government-to-government and business-to-business schemes, including highlighting some case studies for their improvement going forward | Q4 2022–Q2 2024
4. Labor market database and information system developed | Q4 2022–Q4 2024
4.1 Conduct comprehensive assessments or policy analyses on the job and labor market in the region covering labor market and mobility, recruitment policies, and social protection | Q4 2022–Q4 2024

## Slide 14: Next Steps
Conduct call for papers for collaborative research across universities in the CAREC region on key topics of: (i). making the economy more resilience and inclusive (i.e., recovering better and stronger from pandemic) and (ii). improving the overall migration system to better utilize the CAREC workforce.
Creation of cross-country interagency working group comprising of women and men professionals in higher education standardization and harmonization
Prepare bilateral and/or regional framework on higher education standardization and harmonization prepared
Prepare MOU/agreement between two or more regional universities for degree, faculty or student exchange and/or qualification standardization program.

## Slide 15
Thank you!